## Tabelle1
Sprint 1
Sprint 2
Sprint 3
Sprint 4
Sprint 5
Priority | Backlog Item | Task | Details (Wiki, URLs etc.) | Developers | Estimated Effort (1-10) | Effective Effort per Sprint
[6 empty] | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
1 | Knowledge Crunching | Understanding what the game is about |  | ALL | 6
2 |  | Technology Analysis |  | ALL | 6
3 |  | Game Pattern Definition (MVC - GameLoop) |  | ALL | 3
4 | Choose a theme | Choose a theme to develop mechanics accordingly |  | ALL | 1
5 | Continuous Integration | Studying Typical Approaches |  | ALL | 3
6 |  | Implement CI workflow |  | ALL | 5
| Game Entities | Turret |  | Penazzi | 4
|  | Enemy |  | Foschini | 4
|  | Game Field |  | Alpi | 6
| Game Loop |  |  | Parrinello | 8